## Sheet1
Task Name | Estimate time( hour) | Taken by | Actual Time | Status | Date Doing | Note | Problem
List all the possible requirements | 12 | Nguyen Vu Tuan Anh | 48 | Done | 22/10/2020
Create master page for user | 0.25 | Nguyen Vu Tuan Anh |  | Done
Create master page for admin | 0.15 | Nguyen Vu Tuan Anh |  | Done
Create login page | 0.5 | Nguyen Vu Tuan Anh |  | Done
Create register page | 0.5 | Nguyen Vu Tuan Anh |  | Done
Add cakes dynamically from admin side | 0.5 | Nguyen Vu Tuan Anh |  | Done
Display cakes using repeater form database | 1.5 | Nguyen Vu Tuan Anh |  | Done
Display cake's details for each cake | 0.12 | Nguyen Vu Tuan Anh |  | Done
Create shopping cart using cookies | 4 | Nguyen Vu Tuan Anh |  | Done
Delete cake from cart | 2 | Nguyen Vu Tuan Anh |  | Done
Add custom quantity in cart | 1.5 | Nguyen Vu Tuan Anh |  | Done
Reduce/Increase stock when a cake is added/deleted | 3 | Nguyen Vu Tuan Anh |  | Done
Count the total amount of money in cart | 0.12 | Nguyen Vu Tuan Anh |  | Done
Count total of money and cakes in cart using session | 0.5 | Nguyen Vu Tuan Anh |  | Done
Create check out page | 2 | Nguyen Vu Tuan Anh |  | Done
Integrate paypal to payment | 5 | Nguyen Vu Tuan Anh | 8 | Fail |  | Paypal account locked
Display order and order details on admin side | 1 | Nguyen Vu Tuan Anh |  | Done
Display order and order details of user only | 1 | Nguyen Vu Tuan Anh |  | Done
Search cake by name | 0.5 | Nguyen Vu Tuan Anh |  | Done
Total | 36.14